## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name: | Selenium Python Advanced Capstone
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By: | K.Sathwik
Approved By:
SCOPE
Features to be Tested:
1.
2.
TESTING TYPE
Functional Testing | ☐
Regression Testing | ☐
Integration Testing | ☐
UAT | ☐
TEST ENVIRONMENT
Environment: | Dev / QA / Staging / Production
Browser/OS:
TIMELINE
Start Date: | 2026-05-06
End Date:
RESOURCES
QA Lead:
QA Resources:
Test Data Provider:
RISKS & ASSUMPTIONS
Risks:
Assumptions:

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | User login | Verify user can login with valid credentials | User account should exist
SC-002 | Invalid login validation | Verify application handles invalid login attempts properly | Application login page available
SC-003 | Create note successfully | Verify note can be created successfully with valid inputs | User logged in
SC-004 | Instant note display | Verify newly created note appears instantly in UI without refresh | User logged in
SC-005 | Empty note field validation | Verify validation messages appear when note fields are empty | User logged in
SC-006 | GET notes API validation | Verify GET /notes API returns accurate and complete note data | Valid API authentication
SC-007 | Unauthorized API access | Verify API handles unauthorized and invalid requests correctly | API endpoint accessible
SC-008 | UI to API sync | Verify note created in UI appears correctly in API response | User logged in and API auth available
SC-009 | Delete note via API | Verify note can be deleted successfully using API | Existing note available
SC-010 | API to UI sync | Verify API-deleted note disappears from UI correctly | Existing note available
SC-011 | API performance check | Verify API response time is below 2 seconds | API endpoint accessible

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Actual Result | Priority | Status
TC-001 | SC-001 | Login with valid credentials | User account exists | 1. Enter valid username 2. Enter valid password 3. Click Login | User redirected to dashboard successfully | User successfully redirected to dashboard | High | Executed
TC-002 | SC-002 | Login with invalid username | Login page loaded | 1. Enter invalid username 2. Enter valid password 3. Click Login | Error message displayed for invalid username | Error message displayed for invali username | High | Executed
TC-003 | SC-002 | Login with invalid password | Login page loaded | 1. Enter valid username 2. Enter invalid password 3. Click Login | Error message displayed for invalid password | Error message displayed for invalid password | High | Executed
TC-004 | SC-002 | Login with empty fields | Login page loaded | 1. Leave username empty 2. Leave password empty 3. Click Login | Validation message displayed | Validation message displayed | Medium | Executed
TC-005 | SC-005 | Verify dashboard redirect after login | User logged in successfully | 1. Login with valid credentials | User redirected to dashboard page | User successfully redirected to dashboard | High | Executed
TC-006 | SC-003 | Create note with valid details | User logged in | 1. Click Create Note 2. Enter title 3. Enter description 4. Click Save | Note created successfully | Note created successfully | High | Executed
TC-007 | SC-003 | Verify success message after note creation | User logged in | 1. Create a note with valid data 2. Click Save | Success message displayed | No the success message is not displayed after note creation | Medium | Executed
TC-008 | SC-004 | Verify instant note display in UI | User logged in | 1. Create new note 2. Save note | Newly created note displayed instantly without refresh | Yes newly created note displayed instantly without refresh | High | Executed
TC-009 | SC-003 | Create note with large description | User logged in | 1. Enter note title 2. Enter large description 3. Save note | Note created successfully without issues | Note not created with large description | Medium | Executed
TC-010 | SC-005 | Create note with empty fields | User logged in | 1. Click Create Note 2. Leave fields empty 3. Click Save | Validation messages displayed | Validation message displayed | High | Executed
TC-011 | SC-006 | Validate GET /notes API status | Valid API authentication available | 1. Send GET /notes request | API returns status code 200 | Yes API returns status code 200 | High | Executed
TC-012 | SC-006 | Validate notes list from API | Valid API authentication available | 1. Send GET /notes request 2. Check response body | Response contains list of notes | The response contains list of notes | High | Executed
TC-013 | SC-006 | Validate API response note data | Valid API authentication available | 1. Send GET /notes request 2. Verify note fields | API returns accurate and complete note data | API returns accurate and complete note data | High | Executed
TC-014 | SC-007 | Access GET /notes without authentication | API endpoint accessible | 1. Send GET /notes request without token | Unauthorized error returned | Unauthorized error returned | High | Executed
TC-015 | SC-008 | Validate UI to API synchronization | User logged in and API auth available | 1. Create note via UI 2. Call GET /notes API 3. Verify note in response | Created note in ui that should appears in API response | Yes created note using ui appeared in API response | High | Executed
TC-016 | SC-008 | Validate UI and API note field consistency | Existing created note | 1. Create note via UI 2. Fetch note from API 3. Compare title and description | UI and API note fields match | UI and API note fields match | High | Executed
TC-017 | SC-009 | Delete note using API | Existing note available | 1. Send DELETE request for note ID | Note deleted successfully | Note deleted successfully using API | High | Executed
TC-018 | SC-009 | Delete note with invalid ID | Valid API authentication available | 1. Send DELETE request with invalid note ID | Proper error response returned | Proper error response returned with invalid id | Medium | Executed
TC-019 | SC-010 | Validate API to UI synchronization | Existing note available | 1. Delete note via API 2. Refresh UI 3. Verify note removal | Deleted note no longer visible in UI | Deleted note no longer visible in UI | High | Executed
TC-020 | SC-011 | Validate API response performance | API endpoint accessible | 1. Send GET /notes request 2. Measure response time | API response time below 2 seconds | API response time below 2 seconds that is 234ms | Medium | Executed

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Username: sathwikkulkarni123@gmail.com, Password: Capg@123 | Valid login scenarios
TD-002 | Invalid Username | invalid@gmail.com | Used for invalid username validation
TD-003 | Invalid Password | asddsasd | Used for invalid password validation
TD-004 | Empty fields | Username: "" Password: "" | Used for empty username and empty password validation
TD-005 | Valid Note Title | Notes_1 | Used for valid note creation
TD-006 | Valid Note Description | This is my first notes | Used for valid note description input
TD-007 | Large Note Description | Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. Cum sociis natoque penatibus et magnis dis parturient montes, nascetur ridiculus mus. Donec quam felis, ultricies nec, pellentesque eu, pretium quis, sem. Nulla consequat massa quis enim. Donec pede justo, fringilla vel, aliquet nec, vulputate eget, arcu. In enim justo, rhoncus ut, imperdiet a, venenatis vitae, justo. Nullam dictum felis eu pede mollis pretium. Integer tincidunt. Cras dapibus. Vivamus elementum semper nisi. Aenean vulputate eleifend tellus. Aenean leo ligula, porttitor eu, consequat vitae, eleifend ac, enim. Aliquam lorem ante, dapibus in, viverra quis, feugiat a, tellus. Phasellus viverra nulla ut metus varius laoreet. Quisque rutrum. Aenean imperdiet. Etiam ultricies nisi vel augue. Curabitur ullamcorper ultricies nisi. Nam eget dui. Etiam rhoncus. Maecenas tempus, tellus eget condimentum rhoncus, sem quam semper libero, sit amet adipiscing sem neque sed ipsum. Nam quam nunc, blandit vel, luctus pulvinar, hendrerit id, lorem. Maecenas nec odio et ante tincidunt tempus. Donec vitae sapien ut libero venenatis faucibus. Nullam quis ante. Etiam sit amet orci eget eros faucibus tincidunt. Duis leo. Sed fringilla mauris sit amet nibh. Donec sodales sagittis magna. Sed consequat, leo eget bibendum sodales, augue velit cursus nunc, quis gravida magna mi a libero. Fusce vulputate eleifend sapien. Vestibulum purus quam, scelerisque ut, mollis sed, nonummy id, metus. Nullam accumsan lorem in dui. Cras ultricies mi eu turpis hendrerit fringilla. Vestibulum ante ipsum primis in faucibus orci luctus et ultrices posuere cubilia Curae; In ac dui quis mi consectetuer lacinia. Nam pretium turpis et arcu. Duis arcu tortor, suscipit eget, imperdiet nec, imperdiet iaculis, ipsum. Sed aliquam ultrices mauris. Integer ante arcu, accumsan a, consectetuer eget, posuere ut, mauris. Praesent adipiscing. Phasellus ullamcorper ipsum rutrum nunc. Nunc nonummy metus. Vestibulum volutpat pretium libero. Cras id dui. Aenean ut eros et nisl sagittis vestibulum. Nullam nulla eros, ultricies sit amet, nonummy id, imperdiet feugiat, pede. Sed lectus. Donec mollis hendrerit risus. Phasellus nec sem in justo pellentesque facilisis. Etiam imperdiet imperdiet orci. Nunc nec neque. Phasellus leo dolor, tempus non, auctor et, hendrerit quis, nisi. Curabitur ligula sapien, tincidunt non, euismod vitae, posuere imperdiet, leo. Maecenas malesuada. Praesent congue erat at massa. Sed cursus turpis vitae tortor. Donec posuere vulputate arcu. Phasellus accumsan cursus velit. Vestibulum ante ipsum primis in faucibus orci luctus et ultrices posuere cubilia Curae; Sed aliquam, nisi quis porttitor congue, elit erat euismod orci, ac placerat dolor lectus quis orci. Phasellus consectetuer vestibulum elit. Aenean tellus metus, bibendum sed, posuere ac, mattis non, nunc. Vestibulum fringilla pede sit amet augue. In turpis. Pellentesque posuere. Praesent turpis. Aenean posuere, tortor sed cursus feugiat, nunc augue blandit nunc, eu sollicitudin urna dolor sagittis lacus. Donec elit libero, sodales nec, volutpat a, suscipit non, turpis. Nullam sagittis. Suspendisse pulvinar, augue ac venenatis condimentum, sem libero volutpat nibh, nec pellentesque velit pede quis nunc. Vestibulum ante ipsum primis in faucibus orci luctus et ultrices posuere cubilia Curae; Fusce id purus. Ut varius tincidunt libero. Phasellus dolor. Maecenas vestibulum mollis diam. Pellentesque ut neque. Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. In dui magna, posuere eget, vestibulum et, tempor auctor, justo. In ac felis quis tortor malesuada pretium. Pellentesque auctor neque nec urna. Proin sapien ipsum, porta a, auctor quis, euismod ut, mi. Aenean viverra rhoncus pede. Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. Ut non enim eleifend felis pretium feugiat. Vivamus quis mi. Phasellus a est. Phasellus magna. In hac habitasse platea dictumst. Curabitur at lacus ac velit ornare lobortis. Curabitur a felis in nunc fringilla tristique. Morbi mattis ullamcorper velit. Phasellus gravida semper nisi. Nullam vel sem. Pellentesque libero tortor, tincidunt et, tincidunt eget, semper nec, quam. Sed hendrerit. Morbi ac felis. Nunc egestas, augue at pellentesque laoreet, felis eros vehicula leo, at malesuada velit leo quis pede. Donec interdum, metus et hendrerit aliquet, dolor diam sagittis ligula, eget egestas libero turpis vel mi. Nunc nulla. Fusce risus nisl, viverra et, tempor et, pretium in, sapien. Donec venenatis vulputate lorem. Morbi nec metus. Phasellus blandit leo ut odio. Maecenas ullamcorper, dui et placerat feugiat, eros pede varius nisi, condimentum viverra felis nunc et lorem. Sed magna purus, fermentum eu, tincidunt eu, varius ut, felis. In auctor lobortis lacus. Quisque libero metus, condimentum nec, tempor a, commodo mollis, magna. Vestibulum ullamcorper mauris at ligula. Fusce fermentum. Nullam cursus lacinia erat. Praesent blandit laoreet nibh. Fusce convallis metus id felis luctus adipiscing. Pellentesque egestas, neque sit amet convallis pulvinar, justo nulla eleifend augue, ac auctor orci leo non est. Quisque id mi. Ut tincidunt tincidunt erat. Etiam feugiat lorem non metus. Vestibulum dapibus nunc ac augue. Curabitur vestibulum aliquam leo. Praesent egestas neque eu enim. In hac habitasse platea dictumst. Fusce a quam. Etiam ut purus mattis mauris sodales aliquam. Curabitur nisi. Quisque malesuada placerat nisl. Nam ipsum risus, rutrum vitae, vestibulum eu, molestie vel, lacus. Sed augue ipsum, egestas nec, vestibulum et, malesuada adipiscing, dui. Vestibulum facilisis, purus nec pulvinar iaculis, ligula mi congue nunc, vitae euismod ligula urna in dolor. Mauris sollicitudin fermentum libero. Praesent nonummy mi in odio. Nunc interdum lacus sit amet orci. Vestibulum rutrum, mi nec elementum vehicula, eros quam gravida nisl, id fringilla neque ante vel mi. Morbi mollis tellus ac sapien. Phasellus volutpat, metus eget egestas mollis, lacus lacus blandit dui, id egestas quam mauris ut lacus. Fusce vel dui. Sed in libero ut nibh placerat accumsan. Proin faucibus arcu quis ante. In consectetuer turpis ut velit. Nulla sit amet est. Praesent metus tellus, elementum eu, semper a, adipiscing nec, purus. Cras risus ipsum, faucibus ut, ullamcorper id, varius ac, leo. Suspendisse feugiat. Suspendisse enim turpis, dictum sed, iaculis a, condimentum nec, nisi. Praesent nec nisl a purus blandit viverra. Praesent ac massa at ligula laoreet iaculis. Nulla neque dolor, sagittis eget, iaculis quis, molestie non, velit. Mauris turpis nunc, blandit et, volutpat molestie, porta ut, ligula. Fusce pharetra convallis urna. Quisque ut nisi. Donec mi odio, faucibus at, scelerisque quis, convallis in, nisi. Suspendisse non nisl sit amet velit hendrerit rutrum. Ut leo. Ut a nisl id ante tempus hendrerit. Proin pretium, leo ac pellentesque mollis, felis nunc ultrices eros, sed gravida augue augue mollis justo. Suspendisse eu ligula. Nulla facilisi. Donec id justo. Praesent porttitor, nulla vitae posuere iaculis, arcu nisl dignissim dolor, a pretium mi sem ut ipsum. Curabitur suscipit suscipit tellus. Praesent vestibulum dapibus nibh. Etiam iaculis nunc ac metus. Ut id nisl quis enim dignissim sagittis. Etiam sollicitudin, ipsum eu pulvinar rutrum, tellus ipsum laoreet sapien, quis venenatis ante odio sit amet eros. Proin magna. Duis vel nibh at velit scelerisque suscipit. Curabitur turpis. Vestibulum suscipit nulla quis orci. Fusce ac felis sit amet ligula pharetra condimentum. Maecenas egestas arcu quis ligula mattis placerat. Duis lobortis massa imperdiet quam. Suspendisse potenti. Pellentesque commodo eros a enim. Vestibulum turpis sem, aliquet eget, lobortis pellentesque, rutrum eu, nisl. Sed libero. Aliquam erat volutpat. Etiam vitae tortor. Morbi vestibulum volutpat enim. Aliquam eu nunc. Nunc sed turpis. Sed mollis, eros et ultrices tempus, mauris ipsum aliquam libero, non adipiscing dolor urna a orci. Nulla porta dolor. Class aptent taciti sociosqu ad litora torquent per conubia nostra, per inceptos hymenaeos. Pellentesque dapibus hendrerit tortor. Praesent egestas tristique nibh. Sed a libero. Cras varius. Donec vitae orci sed dolor rutrum auctor. Fusce egestas elit eget lorem. Suspendisse nisl elit, rhoncus eget, elementum ac, condimentum eget, diam. Nam at tortor in tellus interdum sagittis. Aliquam lobortis. Donec orci lectus, aliquam ut, faucibus non, euismod id, nulla. Curabitur blandit mollis lacus. Nam adipiscing. Vestibulum eu odio. Vivamus laoreet. Nullam tincidunt adipiscing enim. Phasellus tempus. Proin viverra, ligula sit amet ultrices semper, ligula arcu tristique sapien, a accumsan nisi mauris ac eros. Fusce neque. Suspendisse faucibus, nunc et pellentesque egestas, lacus ante convallis tellus, vitae iaculis lacus elit id tortor. Vivamus aliquet elit ac nisl. Fusce fermentum odio nec arcu. Vivamus euismod mauris. In ut quam vitae odio lacinia tincidunt. Praesent ut ligula non mi varius sagittis. Cras sagittis. Praesent ac sem eget est egestas volutpat. Vivamus consectetuer hendrerit lacus. Cras non dolor. Vivamus in erat ut urna cursus vestibulum. Fusce commodo aliquam arcu. Nam commodo suscipit quam. Quisque id odio. Praesent venenatis metus at tortor pulvinar varius.Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Aenean commodo ligula eget dolor. Aenean massa. Cum sociis natoque penatibus et magnis dis parturient montes, nascetur ridiculus mus. Donec quam felis, ultricies nec, pellentesque eu, pretium quis, sem. Nulla consequat massa quis enim. Donec pede justo, fringilla vel, aliquet nec, vulputate eget, arcu. In enim justo, rhoncus ut, imperdiet a, venenatis vitae, justo. Nullam dictum felis eu pede mollis pretium. Integer tincidunt. Cras dapibus. Vivamus elementum semper nisi. Aenean vulputate eleifend tellus. Aenean leo ligula, porttitor eu, consequat vitae, eleifend ac, enim. Aliquam lorem ante, dapibus in, viverra quis, feugiat a, tellus. Phasellus viverra nulla ut metus varius laoreet. Quisque rutrum. Aenean imperdiet. Etiam ultricies nisi vel augue. Curabitur ullamcorper ultricies nisi. Nam eget dui. Etiam rhoncus. | Used for large text validation
TD-008 | Empty fields for Note creation Note Title | Title :"" Description:"" | Used for empty note title and description validation
TD-009 | API Auth Token | Bearer eyJhbGciOiJIUzI1Ni... | Used for authenticated API requests
TD-010 | Invalid API Token | InvalidToken123 | Used for unauthorized API access validation
TD-011 | GET Notes Endpoint | /notes | Used for GET notes API validation
TD-012 | Invalid Note ID | invalid123 | Used for invalid note deletion validation
TD-013 | UI Created Note Data | Title: Sync Test, Description: API Sync Validation | Used for UI to API synchronization validation
TD-014 | API Response Data | {"title":"Sync Test","description":"API Sync Validation"} | Used for API response comparison validation
TD-015 | API Response Time Threshold | 2 Seconds | Used for API performance validation
TD-016 | Deleted Note Data | Deleted Note Title | Used for API to UI synchronization validation
TD-017 | Sample Unauthorized Request | GET /notes without token | Used for unauthorized access testing

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Login with valid credentials | QA-User1 | 2024-05-05 | Pass |  | Executed successfully
TC-002 | Cycle-1 | Login with invalid username | QA-User1 | 2024-05-05 | Pass |  | Proper error message displayed
TC-003 | Cycle-1 | Login with invalid password | QA-User1 | 2024-05-05 | Pass |  | Proper error message displayed
TC-004 | Cycle-1 | Login with empty fields | QA-User1 | 2024-05-05 | Pass |  | Validation messages displayed correctly
TC-005 | Cycle-1 | Verify dashboard redirect after login | QA-User1 | 2024-05-05 | Pass |  | Redirected to dashboard successfully
TC-006 | Cycle-1 | Create note with valid details | QA-User1 | 2024-05-06 | pass |  | Note created successfully
TC-007 | Cycle-1 | Verify success message after note creation | QA-User1 | 2024-05-06 | Fail | DEF-001 | No message Appeared
TC-008 | Cycle-1 | Verify instant note display in UI | QA-User1 | 2024-05-06 | Pass |  | Note displayed instantly without refresh
TC-009 | Cycle-1 | Create note with large description | QA-User1 | 2024-05-06 | Pass |  | Large description is not handled successfully it acceptes only between 4 to 1000 characters
TC-010 | Cycle-1 | Create note with empty fields | QA-User1 | 2024-05-06 | Pass |  | Validation message is shown for empty fields
TC-011 | Cycle-1 | Validate GET /notes API status | QA-User1 | 2024-05-06 | Pass |  | API returned status code 200
TC-012 | Cycle-1 | Validate notes list from API | QA-User1 | 2024-05-06 | Pass |  | Notes list retrieved successfully
TC-013 | Cycle-1 | Validate API response note data | QA-User1 | 2024-05-06 | Pass |  | API returned accurate note data
TC-014 | Cycle-1 | Access GET /notes without authentication | QA-User1 | 2024-05-06 | Pass |  | Unauthorized access blocked correctly
TC-015 | Cycle-1 | Validate UI to API synchronization | QA-User1 | 2024-05-06 | Pass |  | synchronized correctly between UI and API
TC-016 | Cycle-1 | Validate UI and API note field consistency | QA-User1 | 2024-05-06 | Pass |  | UI and API fields matched correctly
TC-017 | Cycle-1 | Delete note using API | QA-User1 | 2024-05-06 | Pass |  | Note deleted successfully
TC-018 | Cycle-1 | Delete note with invalid ID | QA-User1 | 2024-05-06 | Pass |  | Proper error response returned
TC-019 | Cycle-1 | Validate API to UI synchronization | QA-User1 | 2024-05-06 | Pass |  | Deleted note removed from UI successfully
TC-020 | Cycle-1 | Validate API response performance | QA-User1 | 2024-05-06 | Pass |  | API response time within acceptable limit

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
FR-01 | TC-001, TC-002, TC-003, TC-004, TC-005 | UI login should work | Covered | Complete
FR-02 | TC-006, TC-007, TC-009, TC-010 | Create note via UI | Covered | Complete
FR-03 | TC-008 | Note should appear instantly in UI list | Covered | Complete
FR-04 | TC-011, TC-012, TC-013 | API GET /notes returns list | Covered | Complete
FR-05 | TC-015, TC-016 | UI-created note must appear in API | Covered | Complete
FR-06 | TC-017, TC-018 | Delete note via API | Covered | Complete
FR-07 | TC-019 | Deleted note must disappear from UI | Covered | Complete
FR-08 | TC-020 | API response < 2s | Covered | Complete
FR-09 | TC-002, TC-003, TC-004, TC-010, TC-014, TC-018 | Negative scenarios (UI & API) | Covered | Complete

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-007 | Success message not displayed after note creation | When a note is created successfully, the application does not display the expected success confirmation message to the user | Medium | High | Open | Dev-User1 | 2024-05-06 | Needs investigation

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name:
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By:
EXECUTION SUMMARY
Total Test Cases: | 20
Test Cases Executed: | 20
Test Cases Passed: | 18
Test Cases Failed: | 2
Pass Percentage: | 90
DEFECT SUMMARY
Total Defects: | 2
Critical Defects: | 0
High Defects: | 1
Medium Defects: | 1
Low Defects: | 0
Open Defects: | 2
Closed Defects: | 0
CONCLUSION
Testing Status: | In Progress
Release Readiness: | Pending Defect Resolution
Overall Recommendation: | Not Ready for Production
REMARKS